## Project Cost Estimate
Project Cost Estimate
NOTE: This tool has been simplified for training purposes. Edit yellow cells only. Do not insert or delete rows. The password to unlock this sheet is "elemental".
# | WBS item description | Resources | Labour | Goods/materials | Sub-total
1 | Planning Phase |  |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 | PM during Implementation |  |  |  | 0
8 | Closure Phase |  |  |  | 0
| Budget At Completion (BAC) |  |  |  | 0
|  |  | Project Contingency = |  | 0
| Cost Baseline |  |  |  | 0
|  |  | Management Reserve = |  | 0
| Project Budget |  |  |  | 0
Indirect Cost =
| Project Cost Estimate |  |  |  | 0
Step 2 - define contingency, management reserve, and indirect cost allocations (yellow cells) to determine the Project Cost Estimate
Step 1 - complete the yellow cells. You may leave some rows blank but you can't insert more rows. Capture high-level deliverables from your WBS (summarise all deliverables in up to 5 work packages), ensuring that you have captured all the work in the Implementation Phase, then esimate the labour and goods costs for each.

## Integrated Baseline & EVA
Earned Value Analysis | [6 empty] | Integrated Baseline
NOTE: Edit yellow cells only. Do not insert or delete rows. The password to unlock this sheet is "elemental". | [5 empty] | 0 | [55 empty] | 0
| It is the end of month 7. |  |  |  |  | 0 | [55 empty] | 0
At this point in time, the project's percent complete is… | [5 empty] | 0 | [55 empty] | 0
And actual costs incurred to date are… | [5 empty] | 0 | [55 empty] | 0
Base metrics | [5 empty] | 0 | [55 empty] | 0
Budget at Completion (BAC) = total budgeted direct costs = |  |  | 0 | at end of Month 12. |  | 0 | [55 empty] | 0
Planned Value (PV) = Budgeted Cost of Work Scheduled (BCWS) = |  |  | 0 | at end of Month 7. |  | 0 | [55 empty] | 0
Earned Value (EV) = Budgeted Cost of Work Performed (BCWP) = |  |  | 0 |  |  | 0 | [55 empty] | 0
Actual Cost (AC) = Actual Cost of Work Performed (ACWP) = |  |  | 0 |  |  | 0 | [55 empty] | 0
Variance Analysis | [5 empty] | 0 | [55 empty] | 0
Cost Variance as a percentage (CV%) = (EV-AC)/EV x 100 = |  |  | #DIV/0! | [select from drop-down] |  | 0 | [55 empty] | 0
Schedule Variance as a percentage (SV%) = (EV-PV)/PV x 100 = |  |  | #DIV/0! | [select from drop-down] |  | 0 | [55 empty] | 0
How would you describe project performance to a stakeholder who was not trained in EVM? | [5 empty] | 0 | [55 empty] | 0
[6 empty] | 0 | [55 empty] | 0
[6 empty] | 0 | [55 empty] | 0
Forecasting metrics | [5 empty] | 0 | [55 empty] | 0
Cost Performance Index (CPI) at end of week 7 = EV/AC = |  |  | #DIV/0! |  |  | 0 | [55 empty] | 0
Schedule Performance Index (SPI) at end of week 7 = EV/PV = |  |  | #DIV/0! |  |  | 0 | [55 empty] | 0
Estimate At Completion (iEAC) = [(BAC-EV)/(CPIxSPI)] + AC = |  |  | #DIV/0! |  |  | 0 | [55 empty] | 0
Estimate To Complete (ETC) = EAC – AC = |  |  | #DIV/0! |  |  | 0 | [55 empty] | 0
Variance at Completion (VAC) = BAC – EAC |  |  | #DIV/0! |  |  | 0
How would you summarise forecasted project performance for a stakeholder who was not familiar with EVM? |  |  |  |  | Cumulative total: |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | [7 empty] | <-- When you have finished, this should equal the total direct cost below (BAC)
[5 empty] | Budgeted costs per time-phase: |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
[7 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 (5wks) |  |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 (5wks) |  |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10 (5wks) |  |  |  |  | Month 11 |  |  |  | Month 12
 | time axis 2021-11-08 to 2022-11-21
Project Cost Estimate | time axis 2021-11-08 to 2022-11-21
# | WBS item description | Resources | Labour | Goods | Sub-total | Duration (wks) | 2021-11-08: Month 1; 2021-12-06: Month 2; 2022-01-03: Month 3 (5wks); 2022-02-07: Month 4; 2022-03-07: Month 5; 2022-04-04: Month 6; 2022-05-02: Month 7 (5wks); 2022-06-06: Month 8; 2022-07-04: Month 9; 2022-08-01: Month 10 (5wks); 2022-09-05: Month 11; 2022-10-03: Month 12
1 | Planning Phase |  | 0 | 0 | 0 | 0 | [55 empty] | 0
[7 empty] | 2021-11-08: - - - - - - - - - - - -; 2021-12-06: - - - - - - - - - - - -; 2022-01-03: - - - - - - - - - - - -; 2022-02-07: - - - - - - - - - - - -; 2022-03-07: - - - - - - - - - - - -; 2022-04-04: - - - - - - - - - - - -; 2022-05-02: - - - - - - - - - - - -; 2022-06-06: - - - - - - - - - - - -; 2022-07-04: - - - - - - - - - - - -; 2022-08-01: - - - - - - - - - - - -; 2022-09-05: - - - - - - - - - - - -; 2022-10-03: - - - - - - - - - - - - | 0
2 | 0 |  | 0 | 0 | 0 | 0 | [55 empty] | 0
[7 empty] | 2021-11-08: - - - - - - - - - - - -; 2021-12-06: - - - - - - - - - - - -; 2022-01-03: - - - - - - - - - - - -; 2022-02-07: - - - - - - - - - - - -; 2022-03-07: - - - - - - - - - - - -; 2022-04-04: - - - - - - - - - - - -; 2022-05-02: - - - - - - - - - - - -; 2022-06-06: - - - - - - - - - - - -; 2022-07-04: - - - - - - - - - - - -; 2022-08-01: - - - - - - - - - - - -; 2022-09-05: - - - - - - - - - - - -; 2022-10-03: - - - - - - - - - - - - | 0
3 | 0 |  | 0 | 0 | 0 | 0 | [55 empty] | 0
[7 empty] | 2021-11-08: - - - - - - - - - - - -; 2021-12-06: - - - - - - - - - - - -; 2022-01-03: - - - - - - - - - - - -; 2022-02-07: - - - - - - - - - - - -; 2022-03-07: - - - - - - - - - - - -; 2022-04-04: - - - - - - - - - - - -; 2022-05-02: - - - - - - - - - - - -; 2022-06-06: - - - - - - - - - - - -; 2022-07-04: - - - - - - - - - - - -; 2022-08-01: - - - - - - - - - - - -; 2022-09-05: - - - - - - - - - - - -; 2022-10-03: - - - - - - - - - - - - | 0
4 | 0 |  | 0 | 0 | 0 | 0 | [55 empty] | 0
[7 empty] | 2021-11-08: - - - - - - - - - - - -; 2021-12-06: - - - - - - - - - - - -; 2022-01-03: - - - - - - - - - - - -; 2022-02-07: - - - - - - - - - - - -; 2022-03-07: - - - - - - - - - - - -; 2022-04-04: - - - - - - - - - - - -; 2022-05-02: - - - - - - - - - - - -; 2022-06-06: - - - - - - - - - - - -; 2022-07-04: - - - - - - - - - - - -; 2022-08-01: - - - - - - - - - - - -; 2022-09-05: - - - - - - - - - - - -; 2022-10-03: - - - - - - - - - - - - | 0
5 | 0 |  | 0 | 0 | 0 | 0 | [55 empty] | 0
[7 empty] | 2021-11-08: - - - - - - - - - - - -; 2021-12-06: - - - - - - - - - - - -; 2022-01-03: - - - - - - - - - - - -; 2022-02-07: - - - - - - - - - - - -; 2022-03-07: - - - - - - - - - - - -; 2022-04-04: - - - - - - - - - - - -; 2022-05-02: - - - - - - - - - - - -; 2022-06-06: - - - - - - - - - - - -; 2022-07-04: - - - - - - - - - - - -; 2022-08-01: - - - - - - - - - - - -; 2022-09-05: - - - - - - - - - - - -; 2022-10-03: - - - - - - - - - - - - | 0
6 | 0 |  | 0 | 0 | 0 | 0 | [55 empty] | 0
[7 empty] | 2021-11-08: - - - - - - - - - - - -; 2021-12-06: - - - - - - - - - - - -; 2022-01-03: - - - - - - - - - - - -; 2022-02-07: - - - - - - - - - - - -; 2022-03-07: - - - - - - - - - - - -; 2022-04-04: - - - - - - - - - - - -; 2022-05-02: - - - - - - - - - - - -; 2022-06-06: - - - - - - - - - - - -; 2022-07-04: - - - - - - - - - - - -; 2022-08-01: - - - - - - - - - - - -; 2022-09-05: - - - - - - - - - - - -; 2022-10-03: - - - - - - - - - - - - | 0
7 | PM during Implementation |  | 0 | 0 | 0 | 0 | [55 empty] | 0
[7 empty] | 2021-11-08: - - - - - - - - - - - -; 2021-12-06: - - - - - - - - - - - -; 2022-01-03: - - - - - - - - - - - -; 2022-02-07: - - - - - - - - - - - -; 2022-03-07: - - - - - - - - - - - -; 2022-04-04: - - - - - - - - - - - -; 2022-05-02: - - - - - - - - - - - -; 2022-06-06: - - - - - - - - - - - -; 2022-07-04: - - - - - - - - - - - -; 2022-08-01: - - - - - - - - - - - -; 2022-09-05: - - - - - - - - - - - -; 2022-10-03: - - - - - - - - - - - - | 0
8 | Closure Phase |  | 0 | 0 | 0 | 0 | [55 empty] | 0
[7 empty] | 2021-11-08: - - - - - - - - - - - -; 2021-12-06: - - - - - - - - - - - -; 2022-01-03: - - - - - - - - - - - -; 2022-02-07: - - - - - - - - - - - -; 2022-03-07: - - - - - - - - - - - -; 2022-04-04: - - - - - - - - - - - -; 2022-05-02: - - - - - - - - - - - -; 2022-06-06: - - - - - - - - - - - -; 2022-07-04: - - - - - - - - - - - -; 2022-08-01: - - - - - - - - - - - -; 2022-09-05: - - - - - - - - - - - -; 2022-10-03: - - - - - - - - - - - - | 0
| Budget At Completion (BAC) |  |  |  | 0
|  |  | Project Contingency = | 0% | 0
| Cost Baseline (PM's financial delegation) |  |  |  | 0
|  |  | Management Reserve = | 5% | 0
| Project Budget |  |  |  | 0
|  |  | Indirect Cost = | 15% | 0
| Project Cost Estimate |  |  |  | 0
Following on from Steps 1 and 2 on the Project Cost Estimate tab...
Step 3 - create a high-level Gantt chart by typing either:
"L" in the yellow cells where each activity is planned to occur (to form the bar)
"LG" in the timephase in which the goods are to be received.
Cost estimates will be allocated automatically (labour pro-rated; goods lumped).
Step 4 - check that the number at the end of the cumulative total row is equal to the BAC below
Step 5 - build the integrated baseline by placing these lines according to the cumulative total at the end of each timephase (blue numbers).
Time now
Step 7 - position this line at actual time (end of month 7)
(EV) x
(PV) x
(AC) x
Step 8 - move these data points onto the graph, to show PV, EV, and AC at the end of Month 7
Step 10 - translate EAC, ETC, and VAC into a plain-English summary
Step 9 - select the correct options from these drop-down lists, then translate CV and SV into a plain-English statement that summarises project performance at Month 7
Step 6 - experiment with these figures to see the impact of cost and schedule variance, below